## Gantt
Project Name: | MTA Daily Ridership – Recovery Analysis & Forecast (DEPI Data Analysis Track)
Project Start: | 2026-10-04
Plan End (Phase 2): | 2026-11-06
weeks in progress: | 5
[7 empty] | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01
Phase | Tasks | Responsible Person | Start Date | End Date | Days | Status | 1 | 2 | 3 | 4 | 5
Phase 1 – Management, Planning & Requirements (Due 16 Oct) |  |  | 2026-10-04 | 2026-10-16 | 13
| Create GitHub repo and add all members | Salem | 2026-10-04 | 2026-10-06 | 3 | Done
| Project Proposal (overview, problem, objectives, scope) | Salem | 2026-10-05 | 2026-10-12 | 8 | Done
| Gantt Chart, task distribution & risk plan | Dalia | 2026-10-05 | 2026-10-12 | 8 | Done
| KPIs and success measures | Rana | 2026-10-05 | 2026-10-12 | 8 | Done
| Requirements (stakeholders, user stories, FR/NFR) | Mohamed | 2026-10-05 | 2026-10-12 | 8 | Done
| Group review of all Phase 1 documents | All Team | 2026-10-13 | 2026-10-14 | 2 | Done
| Upload to GitHub and submit Phase 1 | All Team | 2026-10-15 | 2026-10-16 | 2 | Done
Phase 2 – Design & Analysis (Due 6 Nov) |  |  | 2026-10-17 | 2026-11-06 | 21
| Final problem statement and objectives | Salem | 2026-10-17 | 2026-10-20 | 4 | Not Started
| Tech stack (tools and GitHub structure) | Mohamed | 2026-10-19 | 2026-10-22 | 4 | Not Started
| Use Case diagram | Rana | 2026-10-19 | 2026-10-28 | 10 | In Progress
| ERD (star schema: fact + Dim_Date + Dim_Mode) | Mira | 2026-10-19 | 2026-10-30 | 12 | Not Started
| DFD (source → cleaning → analysis → dashboard) | Mohamed | 2026-10-22 | 2026-10-30 | 9 | Not Started
| Wireframe: Overview page | Dalia | 2026-10-26 | 2026-11-03 | 9 | In Progress
| Wireframe: Recovery page | Dalia | 2026-10-26 | 2026-11-03 | 9 | In Progress
| Wireframe: Patterns page | Dalia | 2026-10-26 | 2026-11-03 | 9 | In Progress
| Wireframe: Forecast page | Dalia | 2026-10-26 | 2026-11-03 | 9 | In Progress
| Group review and upload Phase 2 | All Team | 2026-11-04 | 2026-11-06 | 3 | Not Started
Legend:
official deadlines (16 Oct and 6 Nov). Phases 3 and 4 will be added later.

## Task Distribution
Task Distribution
Member | Phase 1,2 deliverable | Total tasks | In Progress | Done | % Done
Salem | Project Proposal + GitHub repo + Final problem statement and objectives | 3 | 0 | 2 | 66.67%
Dalia | Gantt chart, task distribution, risk plan +Wireframes(4 Pages) | 5 | 4 | 1 | 20%
Mohamed | Requirements (stakeholders, user stories, FR/NFR) + Tech stack + DFD | 3 | 0 | 1 | 33.33%
Rana | KPIs and success measures + Use Case diagram | 2 | 1 | 1 | 50%
Mira | ERD (Joined after the Phase 1 split ) | 1 | 0 | 0 | 0%
All Team | Group tasks (reviews, submissions) | 3 | 0 | 2 | 66.67%
Total |  | 17 | 5 | 7 | 41.18%
Counts update automatically from the Gantt sheet (names must match the 'Responsible Person' column).

## Risk Plan
Risk Plan
Probability and Impact: 1 = Low, 2 = Medium, 3 = High. Score = Probability × Impact (1–2 Low, 3–4 Medium, 6–9 High).
ID | Risk | Probability | Impact | Score | Level | Status | Mitigation / Response | Owner
R1 | A team member leaves or becomes inactive | 2 | 3 | 6 | High | Happened | One member left the group. Tasks were redistributed across five members after a new member joined, and every role is documented in the Gantt. If it happens again: redistribute within 48 hours and inform the trainer. | Salem
R2 | A deadline is missed (16 Oct, 6 Nov, 30 Nov, 4 Dec) | 2 | 3 | 6 | High | Open | Internal draft deadlines 3–4 days before each official date; weekly meeting; anyone blocked says so early in the group. | Salem
R3 | Data model delivered late blocks all dashboard pages | 2 | 3 | 6 | High | Open | The cleaned model is due on 12 Nov. Meanwhile the others work on wireframes and draft measures; escalate in the group if it is not shared by 12 Nov. | All Team
R4 | Forecast accuracy is low | 2 | 2 | 4 | Medium | Open | Use 2022 onward only (exclude COVID years); backtest on the last 3 months; compare with a same-month-last-year baseline; document limits honestly. | All Team
R5 | Power BI files conflict when pages are merged | 3 | 2 | 6 | High | Open | One person owns and merges the main .pbix; everyone builds from the same cleaned model; name versions with the date. | All Team
R6 | Data quality issues (zero values in Staten Island, different units for Access-A-Ride and Bridges & Tunnels) | 3 | 1 | 3 | Medium | Open | Treat the zero days as missing; show different units separately; document every cleaning step. | All Team
R7 | GitHub mistakes or an unclear commit history | 2 | 2 | 4 | Medium | Open | One person creates the repo and a short how-to; everyone tests one push in week 1; clear commit messages per member. | Salem
R8 | Unequal workload or invisible individual contribution | 2 | 2 | 4 | Medium | Open | Per-person tasks in the Gantt; weekly check-in; every member explains their own part before the final presentation. | All Team
R9 | Skill gaps (DAX, forecasting in Power BI) | 2 | 2 | 4 | Medium | Open | Weekly short knowledge-sharing; use Power BI's built-in forecast first; ask the trainer when stuck. | All Team
R10 | New member needs onboarding | 2 | 1 | 2 | Low | Open | Short briefing on the project and data; a clear first task; review of the Phase 1 files. | Salem